## Sheet1
ATPS - Test Log
S.no | Screen | Issue Description | Type | Status | Date | Priority
1 | Employee | Able to create Employee with duplicate Email ID | Bug | Fixed | 2017-09-01 | High
2 | Employee | While editing Employee, Last name place holder name is displaying wrongly | Bug | Fixed | 2017-09-01 | Medium
3 | Employee | While editing Employee DOJ is not proper format | Bug | Fixed | 2017-09-01 | Medium
4 | Employee | While creating Employee , alert coming for secondary number field. | Bug | Fixed | 2017-09-01 | Medium
5 | Supplier List | While creating Supplier List, alert coming for Secondary contact number. | Bug | Fixed | 2017-09-01 | Medium
6 | Priority | Allows empty value while editing | Bug | Fixed | 2017-09-01 | High
7 | Customer | Customer Add is not working | Bug | Fixed | 2016-06-01 | High
8 | Customer | Customer Edit is not working | Bug | Fixed | 2016-06-01 | High
9 | Role List | Inappropriate alert message coming with number while editing Role List | Bug | Fixed | 2016-06-01 | Medium
10 | Role List | While editing Role List old value is not reflecting(Showing all vales empty) | Bug | Fixed | 2016-06-01 | Medium
11 | Prority List | While editing Priority List old value is not displaying | Bug | Fixed | 2016-06-01 | Medium
12 | Request Type | Request Type List is not Updated | Bug | Fixed | 2016-06-01 | Medium
13 | Ticket Status | While editing Ticket Status old values is not displaying | Bug | Fixed | 2016-06-01 | Medium
14 | Add Employee | Email validation needed | Bug | Fixed | 2016-12-28 | Medium
15 | General | Over all alert message is not apropriate (Content need to change) | Bug | Fixed | 2016-12-28 | High
16 | General | Need loader symbol wherever sumbit action takes place | Bug | Fixed | 2016-12-28 | Medium
17 | Login | Forget password mail is not working | Bug | Fixed | 2016-12-28 | High
18 | Employee List | Date of Joining format is not proper | Bug | Fixed | 2016-12-28 | Medium
19 | Add Employee | Primary contact number need to validate | Bug | Fixed | 2016-12-28 | Medium
20 | Employee View | Allignment is not proper in Employee View | Bug | Fixed | 2016-12-28 | Medium
21 | Login | While Clicking profile, automatically its log out | Bug | Fixed | 2016-12-28 | High
22 | Login and Forget | While giving emty credentails, need alert message | Bug | Fixed | 2016-12-28 | Medium
23 | Forget | It would be better if the Login button is in Forget password window | Improvement | Fixed | 2016-12-28 | Low
24 | Employee List | Date Of Joining search filter having Default value | Bug | Open | 19-01-2017 | Medium | open
25 | Employee List | Need to validate Date of Joining search field | Bug | Open | 19-01-2017 | Medium
26 | Employee List | While removing the values in Date of Joining search filter it removes the all values is List | Bug | Open | 19-01-2017 | Medium
27 | Customer List | Unable to delete the customer | Bug | Open | 19-01-2017 | High
28 | Customer List | While removing the values in Secondary Number search filter it removes the all values in the list | Bug | Open | 19-01-2017 | Medium
29 | Customer List | While removing the values in City search filter it removes the all values in the list | Bug | Open | 19-01-2017 | Medium
30 | Supplier List | While removing the values in Secondary Number search filter it removes the all values in the list | Bug | Open | 19-01-2017 | Medium
31 | Supplier List | While removing the values in City search filter it removes the all values in the list | Bug | Open | 19-01-2017 | Medium
32 | Role Master | Created date Filter is not working | Bug | Open | 19-01-2017 | Medium
33 | Priority Master | Created date Filter is not working | Bug | Open | 19-01-2017 | Medium
34 | Priority Master | Unable to reset the Created Date filter value | Bug | Open | 19-01-2017 | Medium
35 | Priority Master | Wrong toaster coming while editing the Priority master | Bug | Open | 19-01-2017 | High
36 | Sub category | Select place holder is not coming in Ticket Category name drop down | Bug | Open | 19-01-2017 | Medium