## Sheet1
ESTIMATION
Sr. No | ERP - Enhancements / Improvements | Module Name | Front End (Hours) | Back End (Hours) | Date Of Complete(Back End) | Date Of Complete(Front End) | Status(Front End) | Status(Back End)
1 | Suggested to show the Error message description,Summary (Count) to display the matching and unmatched line items | BulkCSI | 5 | 8 | 16-08-2017,17-08-2017 | 2017-08-17 |  | WIP
2 | Shrinkage in CDN round off to be changed to 0.25 from 0.5 | CDN | 5 |  |  | 2017-08-16 | completed
3 | Ooty and palada dropdown for all dc | STI |  | 10min | 2017-08-17
4 | Shrinkage data will be System Stock - Physical Stock | Physical stock |  | 1 | 2017-08-17
5 | Route master must be created | New | 5 | 5 | 2017-08-17 | 16-08-2017,18-08-2017 | WIP
6 | Mapping Route with Sales Person | New | 5 | 4 | 18-08-2017,21-08-2017 | 16-08-2017,22-08-2017 | WIP
7 | Customer master entry for the combination of route and sales person | Customer master | 1 | 2 | 18-08-2017,21-08-2017 | 2017-08-21
8 | On CDN, filtering of CSI based on route/sales person, in which sales person is to be fetched from csi created. | CDN | 5 | 4 | 18-08-2017,21-08-2017 | 2017-08-21
9 | Discussed about Date and Time based stock summary. | Summary |  | 2 | 2017-08-16 |  |  | WIP
10 | Comport based data capture Connection – Backup for Bluetooth | Barcode |  | 8
11 | System stock must be updated as per physical stock after approval of physical stock | Physical stock | 2 | 4 | 18-08-2017,21-08-2017 | 2017-08-21
12 | Customer template mapping - export and import with excel -based on customer | Barcode | 6 | 8 | 22-08-2017,23-08-2017 | 22-08-2017,23-08-2017
13 | Consolidated DC Wise CSI view - with excel download option. | New | 5 | 3 | 2017-08-24 | 24-08-2017,28-08-2017
14 | Based on shrinkage report batch: stock to be updated, reversed in case of request and during this process all transactions must be blocked(alert is to be given) | Physical stock | 2 | 5 | 2017-08-24 | 2017-08-28
15 | Grn validation for zero quantity (Billed Quantity) | GRN | 2 |  |  | 2017-08-28
Total(Hours) |  |  | 43 | 54